## Details
COMMISSIONING GENERATION TEST DETAILS | [7 empty] | USER INSTRUCTIONS
GENERATOR DETAILS
[8 empty] | 1 | This spreadsheet must be completed and submitted to Market Operations to be regarded as a valid request for a Commissioning Test for a facility.
Market Participant: | Mumbida Wind Farm
[8 empty] | 2 | Data entry is restricted to the areas highlighted in yellow, which have built-in automatic checks to validate entered data.
Facility Designation: | Wind Farm
[8 empty] | 3 | Incomplete Commissioning Test Plan Templates can not be saved. To complete please enter participant & facility names, outage number, start & end dates, and test purpose & description.
Contact Details: |  | Operational |  |  | Commercial
| Email | heath.lang@mumbidawindfarm.com.au |  |  | phil.hyde@mumbidawindfarm.com.au |  |  | 4 | For commissioning tests exceeding one trading day, please make copies of 'Day1' and rename as required.
| Mobile | 0419149751 |  |  | 0419192195
| Phone | 94241807 |  |  | 93221616 |  |  | 5 | Separate Commissioning Test Plan Templates are required to be completed for each facility registered in the market.
| Fax | 94241899 |  |  | 94241899
[8 empty] | 6 | Please email all completed Commissioning Test Plan Templates to Market Operations, Market.operations@westernpower.com.au
Fuel Types: | Fuel "1" |  |  | Fuel "2" |  | Fuel "3"
| na |  |  | na |  | na
TEST DETAILS
Associated Outage No: | 0
Test Period: | Start Date |  | Start Time |  | End Date |  | End Time
| 2013-03-04 |  | 8:00 |  | 2013-04-29 |  | 8:00
Purpose of Test: | Commissioning of the wind farm once backfeed is available. WTGs will be brought online as the day to day description. Initial 27.5 MW constraint to be removed on day 15. WTGs will be curtailed to not exceed this limit.
Test Description | Testing will be as per the GE up tower and downtower commissioning procedures as per the commissioning plan.
System Under Test: | Individual turbines per the day to day testing regime.
Contingency Plan: | Wind farm will be curtailed to the MW setpoint at the point of connection.

## Day1
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-11 | 8:00 | 0 | 0 | na & na & na | low |  |  | WTG online. Tables A11.1 and A11.2 not applicable to Mumbida. Western Power will provide a separate test plan for Mumbida wind farm.
2013-03-11 | 8:30 | 0 | 0 | na & na & na | low |  |  | MW / WTG
2013-03-11 | 9:00 | 0 | 0 | na & na & na | low |  |  | 0
2013-03-11 | 9:30 | 0 | 0 | na & na & na | low |  |  | REACTIVE / WTG
2013-03-11 | 10:00 | 0 | 0 | na & na & na | low |  |  | 0
2013-03-11 | 10:30 | 0 | 0 | na & na & na | low |  |  | No. WTG
2013-03-11 | 11:00 | 0 | 0 | na & na & na | low |  |  | 0
2013-03-11 | 11:30 | 0 | 0 | na & na & na | low
2013-03-11 | 12:00 | 0 | 0 | na & na & na | low
2013-03-11 | 12:30 | 0 | 0 | na & na & na | low
2013-03-11 | 13:00 | 0 | 0 | na & na & na | low
2013-03-11 | 13:30 | 0 | 0 | na & na & na | low
2013-03-11 | 14:00 | 0 | 0 | na & na & na | low
2013-03-11 | 14:30 | 0 | 0 | na & na & na | low
2013-03-11 | 15:00 | 0 | 0 | na & na & na | low
2013-03-11 | 15:30 | 0 | 0 | na & na & na | low
2013-03-11 | 16:00 | 0 | 0 | na & na & na | low
2013-03-11 | 16:30 | 0 | 0 | na & na & na | low
2013-03-11 | 17:00 | 0 | 0 | na & na & na | low
2013-03-11 | 17:30 | 0 | 0 | na & na & na | low
2013-03-11 | 18:00 | 0 | 0 | na & na & na | low
2013-03-11 | 18:30 | 0 | 0 | na & na & na | low
2013-03-11 | 19:00 | 0 | 0 | na & na & na | low
2013-03-11 | 19:30 | 0 | 0 | na & na & na | low
2013-03-11 | 20:00 | 0 | 0 | na & na & na | low
2013-03-11 | 20:30 | 0 | 0 | na & na & na | low
2013-03-11 | 21:00 | 0 | 0 | na & na & na | low
2013-03-11 | 21:30 | 0 | 0 | na & na & na | low
2013-03-11 | 22:00 | 0 | 0 | na & na & na | low
2013-03-11 | 22:30 | 0 | 0 | na & na & na | low
2013-03-11 | 23:00 | 0 | 0 | na & na & na | low
2013-03-11 | 23:30 | 0 | 0 | na & na & na | low
2013-03-12 | 24:00 | 0 | 0 | na & na & na | low
2013-03-12 | 24:30 | 0 | 0 | na & na & na | low
2013-03-12 | 25:00 | 0 | 0 | na & na & na | low
2013-03-12 | 25:30 | 0 | 0 | na & na & na | low
2013-03-12 | 26:00 | 0 | 0 | na & na & na | low
2013-03-12 | 26:30 | 0 | 0 | na & na & na | low
2013-03-12 | 27:00 | 0 | 0 | na & na & na | low
2013-03-12 | 27:30 | 0 | 0 | na & na & na | low
2013-03-12 | 28:00 | 0 | 0 | na & na & na | low
2013-03-12 | 28:30 | 0 | 0 | na & na & na | low
2013-03-12 | 29:00 | 0 | 0 | na & na & na | low
2013-03-12 | 29:30 | 0 | 0 | na & na & na | low
2013-03-12 | 30:00 | 0 | 0 | na & na & na | low
2013-03-12 | 30:30 | 0 | 0 | na & na & na | low
2013-03-12 | 31:00 | 0 | 0 | na & na & na | low
2013-03-12 | 31:30 | 0 | 0 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 2
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-12 | 8:00 | 0 | 0 | na & na & na | low |  |  | WTG online. Tables A11.1 and A11.2 not applicable to Mumbida. Western Power will provide a separate test plan for Mumbida wind farm.
2013-03-12 | 8:30 | 0 | 0 | na & na & na | low |  |  | MW / WTG
2013-03-12 | 9:00 | 0 | 0 | na & na & na | low |  |  | 0
2013-03-12 | 9:30 | 0 | 0 | na & na & na | low |  |  | REACTIVE / WTG
2013-03-12 | 10:00 | 0 | 0 | na & na & na | low |  |  | 0
2013-03-12 | 10:30 | 0 | 0 | na & na & na | low |  |  | No. WTG
2013-03-12 | 11:00 | 0 | 0 | na & na & na | low |  |  | 0
2013-03-12 | 11:30 | 0 | 0 | na & na & na | low
2013-03-12 | 12:00 | 0 | 0 | na & na & na | low
2013-03-12 | 12:30 | 0 | 0 | na & na & na | low
2013-03-12 | 13:00 | 0 | 0 | na & na & na | low
2013-03-12 | 13:30 | 0 | 0 | na & na & na | low
2013-03-12 | 14:00 | 0 | 0 | na & na & na | low
2013-03-12 | 14:30 | 0 | 0 | na & na & na | low
2013-03-12 | 15:00 | 0 | 0 | na & na & na | low
2013-03-12 | 15:30 | 0 | 0 | na & na & na | low
2013-03-12 | 16:00 | 0 | 0 | na & na & na | low
2013-03-12 | 16:30 | 0 | 0 | na & na & na | low
2013-03-12 | 17:00 | 0 | 0 | na & na & na | low
2013-03-12 | 17:30 | 0 | 0 | na & na & na | low
2013-03-12 | 18:00 | 0 | 0 | na & na & na | low
2013-03-12 | 18:30 | 0 | 0 | na & na & na | low
2013-03-12 | 19:00 | 0 | 0 | na & na & na | low
2013-03-12 | 19:30 | 0 | 0 | na & na & na | low
2013-03-12 | 20:00 | 0 | 0 | na & na & na | low
2013-03-12 | 20:30 | 0 | 0 | na & na & na | low
2013-03-12 | 21:00 | 0 | 0 | na & na & na | low
2013-03-12 | 21:30 | 0 | 0 | na & na & na | low
2013-03-12 | 22:00 | 0 | 0 | na & na & na | low
2013-03-12 | 22:30 | 0 | 0 | na & na & na | low
2013-03-12 | 23:00 | 0 | 0 | na & na & na | low
2013-03-12 | 23:30 | 0 | 0 | na & na & na | low
2013-03-13 | 24:00 | 0 | 0 | na & na & na | low
2013-03-13 | 24:30 | 0 | 0 | na & na & na | low
2013-03-13 | 25:00 | 0 | 0 | na & na & na | low
2013-03-13 | 25:30 | 0 | 0 | na & na & na | low
2013-03-13 | 26:00 | 0 | 0 | na & na & na | low
2013-03-13 | 26:30 | 0 | 0 | na & na & na | low
2013-03-13 | 27:00 | 0 | 0 | na & na & na | low
2013-03-13 | 27:30 | 0 | 0 | na & na & na | low
2013-03-13 | 28:00 | 0 | 0 | na & na & na | low
2013-03-13 | 28:30 | 0 | 0 | na & na & na | low
2013-03-13 | 29:00 | 0 | 0 | na & na & na | low
2013-03-13 | 29:30 | 0 | 0 | na & na & na | low
2013-03-13 | 30:00 | 0 | 0 | na & na & na | low
2013-03-13 | 30:30 | 0 | 0 | na & na & na | low
2013-03-13 | 31:00 | 0 | 0 | na & na & na | low
2013-03-13 | 31:30 | #VALUE! | #VALUE! | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 3
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-13 | 8:00 | 0 | 0 | na & na & na | low |  |  | WTG online. Tables A11.1 and A11.2 not applicable to Mumbida. Western Power will provide a separate test plan for Mumbida wind farm.
2013-03-13 | 8:30 | 0 | 0 | na & na & na | low |  |  | MW / WTG
2013-03-13 | 9:00 | 0 | 0 | na & na & na | low |  |  | 2.5
2013-03-13 | 9:30 | 0 | 0 | na & na & na | low |  |  | REACTIVE / WTG
2013-03-13 | 10:00 | 0 | 0 | na & na & na | low |  |  | 0.82
2013-03-13 | 10:30 | 0 | 0 | na & na & na | low |  |  | No. WTG
2013-03-13 | 11:00 | 0 | 0 | na & na & na | low |  |  | 2
2013-03-13 | 11:30 | 0 | 0 | na & na & na | low
2013-03-13 | 12:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 12:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 13:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 13:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 14:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 14:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 15:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 15:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 16:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 16:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 17:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 17:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 18:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 18:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 19:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 19:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 20:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 20:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 21:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 21:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 22:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 22:30 | 5 | 1.64 | na & na & na | low
2013-03-13 | 23:00 | 5 | 1.64 | na & na & na | low
2013-03-13 | 23:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 24:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 24:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 25:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 25:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 26:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 26:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 27:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 27:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 28:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 28:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 29:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 29:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 30:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 30:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 31:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 31:30 | 5 | 1.64 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 4
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-14 | 8:00 | 5 | 1.64 | na & na & na | low |  |  | WTG online. Tables A11.1 and A11.2 not applicable to Mumbida. Western Power will provide a separate test plan for Mumbida wind farm.
2013-03-14 | 8:30 | 5 | 1.64 | na & na & na | low |  |  | MW / WTG
2013-03-14 | 9:00 | 5 | 1.64 | na & na & na | low |  |  | 2.5
2013-03-14 | 9:30 | 5 | 1.64 | na & na & na | low |  |  | REACTIVE / WTG
2013-03-14 | 10:00 | 5 | 1.64 | na & na & na | low |  |  | 0.82
2013-03-14 | 10:30 | 5 | 1.64 | na & na & na | low |  |  | No. WTG
2013-03-14 | 11:00 | 5 | 1.64 | na & na & na | low |  |  | 2
2013-03-14 | 11:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 12:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 12:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 13:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 13:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 14:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 14:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 15:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 15:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 16:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 16:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 17:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 17:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 18:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 18:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 19:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 19:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 20:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 20:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 21:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 21:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 22:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 22:30 | 5 | 1.64 | na & na & na | low
2013-03-14 | 23:00 | 5 | 1.64 | na & na & na | low
2013-03-14 | 23:30 | 5 | 1.64 | na & na & na | low
2013-03-15 | 24:00 | 5 | 1.64 | na & na & na | low
2013-03-15 | 24:30 | 5 | 1.64 | na & na & na | low
2013-03-15 | 25:00 | 5 | 1.64 | na & na & na | low
2013-03-15 | 25:30 | 5 | 1.64 | na & na & na | low
2013-03-15 | 26:00 | 5 | 1.64 | na & na & na | low
2013-03-15 | 26:30 | 5 | 1.64 | na & na & na | low
2013-03-15 | 27:00 | 5 | 1.64 | na & na & na | low
2013-03-15 | 27:30 | 5 | 1.64 | na & na & na | low
2013-03-15 | 28:00 | 5 | 1.64 | na & na & na | low
2013-03-15 | 28:30 | 5 | 1.64 | na & na & na | low
2013-03-15 | 29:00 | 5 | 1.64 | na & na & na | low
2013-03-15 | 29:30 | 5 | 1.64 | na & na & na | low
2013-03-15 | 30:00 | 5 | 1.64 | na & na & na | low
2013-03-15 | 30:30 | 5 | 1.64 | na & na & na | low
2013-03-15 | 31:00 | 5 | 1.64 | na & na & na | low
2013-03-15 | 31:30 | #VALUE! | #VALUE! | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 5
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-15 | 8:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 8:30 | 10 | 3.28 | na & na & na | low |  |  | 2.5
2013-03-15 | 9:00 | 10 | 3.28 | na & na & na | low |  |  | 0.82
2013-03-15 | 9:30 | 10 | 3.28 | na & na & na | low |  |  | 4
2013-03-15 | 10:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 10:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 11:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 11:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 12:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 12:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 13:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 13:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 14:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 14:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 15:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 15:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 16:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 16:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 17:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 17:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 18:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 18:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 19:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 19:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 20:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 20:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 21:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 21:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 22:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 22:30 | 10 | 3.28 | na & na & na | low
2013-03-15 | 23:00 | 10 | 3.28 | na & na & na | low
2013-03-15 | 23:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 24:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 24:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 25:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 25:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 26:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 26:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 27:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 27:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 28:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 28:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 29:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 29:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 30:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 30:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 31:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 31:30 | 10 | 3.28 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 6
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-16 | 8:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 8:30 | 10 | 3.28 | na & na & na | low |  |  | 2.5
2013-03-16 | 9:00 | 10 | 3.28 | na & na & na | low |  |  | 0.82
2013-03-16 | 9:30 | 10 | 3.28 | na & na & na | low |  |  | 4
2013-03-16 | 10:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 10:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 11:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 11:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 12:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 12:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 13:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 13:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 14:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 14:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 15:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 15:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 16:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 16:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 17:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 17:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 18:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 18:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 19:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 19:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 20:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 20:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 21:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 21:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 22:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 22:30 | 10 | 3.28 | na & na & na | low
2013-03-16 | 23:00 | 10 | 3.28 | na & na & na | low
2013-03-16 | 23:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 24:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 24:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 25:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 25:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 26:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 26:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 27:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 27:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 28:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 28:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 29:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 29:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 30:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 30:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 31:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 31:30 | 10 | 3.28 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 7
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-17 | 8:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 8:30 | 10 | 3.28 | na & na & na | low |  |  | 2.5
2013-03-17 | 9:00 | 10 | 3.28 | na & na & na | low |  |  | 0.82
2013-03-17 | 9:30 | 10 | 3.28 | na & na & na | low |  |  | 4
2013-03-17 | 10:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 10:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 11:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 11:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 12:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 12:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 13:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 13:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 14:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 14:30 | 10 | 3.28 | na & na & na | low |  |  | 0.82
2013-03-17 | 15:00 | 10 | 3.28 | na & na & na | low |  |  | 4
2013-03-17 | 15:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 16:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 16:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 17:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 17:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 18:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 18:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 19:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 19:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 20:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 20:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 21:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 21:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 22:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 22:30 | 10 | 3.28 | na & na & na | low
2013-03-17 | 23:00 | 10 | 3.28 | na & na & na | low
2013-03-17 | 23:30 | 10 | 3.28 | na & na & na | low
2013-03-18 | 24:00 | 10 | 3.28 | na & na & na | low
2013-03-18 | 24:30 | 10 | 3.28 | na & na & na | low
2013-03-18 | 25:00 | 10 | 3.28 | na & na & na | low
2013-03-18 | 25:30 | 10 | 3.28 | na & na & na | low
2013-03-18 | 26:00 | 10 | 3.28 | na & na & na | low
2013-03-18 | 26:30 | 10 | 3.28 | na & na & na | low
2013-03-18 | 27:00 | 10 | 3.28 | na & na & na | low
2013-03-18 | 27:30 | 10 | 3.28 | na & na & na | low
2013-03-18 | 28:00 | 10 | 3.28 | na & na & na | low
2013-03-18 | 28:30 | 10 | 3.28 | na & na & na | low
2013-03-18 | 29:00 | 10 | 3.28 | na & na & na | low
2013-03-18 | 29:30 | 10 | 3.28 | na & na & na | low
2013-03-18 | 30:00 | 10 | 3.28 | na & na & na | low
2013-03-18 | 30:30 | 10 | 3.28 | na & na & na | low
2013-03-18 | 31:00 | 10 | 3.28 | na & na & na | low
2013-03-18 | 31:30 | 10 | 3.28 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 8
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-18 | 8:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 8:30 | 12.5 | 4.1 | na & na & na | low |  |  | 2.5
2013-03-18 | 9:00 | 12.5 | 4.1 | na & na & na | low |  |  | 0.82
2013-03-18 | 9:30 | 12.5 | 4.1 | na & na & na | low |  |  | 5
2013-03-18 | 10:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 10:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 11:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 11:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 12:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 12:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 13:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 13:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 14:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 14:30 | 12.5 | 4.1 | na & na & na | low |  |  | 0.82
2013-03-18 | 15:00 | 12.5 | 4.1 | na & na & na | low |  |  | 5
2013-03-18 | 15:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 16:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 16:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 17:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 17:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 18:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 18:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 19:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 19:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 20:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 20:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 21:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 21:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 22:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 22:30 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 23:00 | 12.5 | 4.1 | na & na & na | low
2013-03-18 | 23:30 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 24:00 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 24:30 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 25:00 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 25:30 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 26:00 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 26:30 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 27:00 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 27:30 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 28:00 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 28:30 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 29:00 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 29:30 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 30:00 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 30:30 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 31:00 | 12.5 | 4.1 | na & na & na | low
2013-03-19 | 31:30 | 12.5 | 4.1 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 9
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-19 | 8:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 8:30 | 15 | 4.92 | na & na & na | low |  |  | 2.5
2013-03-19 | 9:00 | 15 | 4.92 | na & na & na | low |  |  | 0.82
2013-03-19 | 9:30 | 15 | 4.92 | na & na & na | low |  |  | 6
2013-03-19 | 10:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 10:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 11:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 11:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 12:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 12:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 13:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 13:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 14:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 14:30 | 15 | 4.92 | na & na & na | low |  |  | 0.82
2013-03-19 | 15:00 | 15 | 4.92 | na & na & na | low |  |  | 6
2013-03-19 | 15:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 16:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 16:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 17:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 17:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 18:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 18:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 19:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 19:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 20:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 20:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 21:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 21:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 22:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 22:30 | 15 | 4.92 | na & na & na | low
2013-03-19 | 23:00 | 15 | 4.92 | na & na & na | low
2013-03-19 | 23:30 | 15 | 4.92 | na & na & na | low
2013-03-20 | 24:00 | 15 | 4.92 | na & na & na | low
2013-03-20 | 24:30 | 15 | 4.92 | na & na & na | low
2013-03-20 | 25:00 | 15 | 4.92 | na & na & na | low
2013-03-20 | 25:30 | 15 | 4.92 | na & na & na | low
2013-03-20 | 26:00 | 15 | 4.92 | na & na & na | low
2013-03-20 | 26:30 | 15 | 4.92 | na & na & na | low
2013-03-20 | 27:00 | 15 | 4.92 | na & na & na | low
2013-03-20 | 27:30 | 15 | 4.92 | na & na & na | low
2013-03-20 | 28:00 | 15 | 4.92 | na & na & na | low
2013-03-20 | 28:30 | 15 | 4.92 | na & na & na | low
2013-03-20 | 29:00 | 15 | 4.92 | na & na & na | low
2013-03-20 | 29:30 | 15 | 4.92 | na & na & na | low
2013-03-20 | 30:00 | 15 | 4.92 | na & na & na | low
2013-03-20 | 30:30 | 15 | 4.92 | na & na & na | low
2013-03-20 | 31:00 | 15 | 4.92 | na & na & na | low
2013-03-20 | 31:30 | 15 | 4.92 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 10
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-20 | 8:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 8:30 | 17.5 | 5.74 | na & na & na | low |  |  | 2.5
2013-03-20 | 9:00 | 17.5 | 5.74 | na & na & na | low |  |  | 0.82
2013-03-20 | 9:30 | 17.5 | 5.74 | na & na & na | low |  |  | 7
2013-03-20 | 10:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 10:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 11:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 11:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 12:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 12:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 13:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 13:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 14:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 14:30 | 17.5 | 5.74 | na & na & na | low |  |  | 0.82
2013-03-20 | 15:00 | 17.5 | 5.74 | na & na & na | low |  |  | 7
2013-03-20 | 15:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 16:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 16:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 17:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 17:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 18:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 18:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 19:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 19:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 20:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 20:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 21:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 21:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 22:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 22:30 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 23:00 | 17.5 | 5.74 | na & na & na | low
2013-03-20 | 23:30 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 24:00 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 24:30 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 25:00 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 25:30 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 26:00 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 26:30 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 27:00 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 27:30 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 28:00 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 28:30 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 29:00 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 29:30 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 30:00 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 30:30 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 31:00 | 17.5 | 5.74 | na & na & na | low
2013-03-21 | 31:30 | 17.5 | 5.74 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 11
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-21 | 8:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 8:30 | 20 | 6.56 | na & na & na | low |  |  | 2.5
2013-03-21 | 9:00 | 20 | 6.56 | na & na & na | low |  |  | 0.82
2013-03-21 | 9:30 | 20 | 6.56 | na & na & na | low |  |  | 8
2013-03-21 | 10:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 10:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 11:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 11:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 12:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 12:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 13:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 13:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 14:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 14:30 | 20 | 6.56 | na & na & na | low |  |  | 0.82
2013-03-21 | 15:00 | 20 | 6.56 | na & na & na | low |  |  | 8
2013-03-21 | 15:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 16:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 16:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 17:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 17:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 18:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 18:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 19:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 19:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 20:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 20:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 21:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 21:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 22:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 22:30 | 20 | 6.56 | na & na & na | low
2013-03-21 | 23:00 | 20 | 6.56 | na & na & na | low
2013-03-21 | 23:30 | 20 | 6.56 | na & na & na | low
2013-03-22 | 24:00 | 20 | 6.56 | na & na & na | low
2013-03-22 | 24:30 | 20 | 6.56 | na & na & na | low
2013-03-22 | 25:00 | 20 | 6.56 | na & na & na | low
2013-03-22 | 25:30 | 20 | 6.56 | na & na & na | low
2013-03-22 | 26:00 | 20 | 6.56 | na & na & na | low
2013-03-22 | 26:30 | 20 | 6.56 | na & na & na | low
2013-03-22 | 27:00 | 20 | 6.56 | na & na & na | low
2013-03-22 | 27:30 | 20 | 6.56 | na & na & na | low
2013-03-22 | 28:00 | 20 | 6.56 | na & na & na | low
2013-03-22 | 28:30 | 20 | 6.56 | na & na & na | low
2013-03-22 | 29:00 | 20 | 6.56 | na & na & na | low
2013-03-22 | 29:30 | 20 | 6.56 | na & na & na | low
2013-03-22 | 30:00 | 20 | 6.56 | na & na & na | low
2013-03-22 | 30:30 | 20 | 6.56 | na & na & na | low
2013-03-22 | 31:00 | 20 | 6.56 | na & na & na | low
2013-03-22 | 31:30 | 20 | 6.56 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 12
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-22 | 8:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 8:30 | 25 | 8.2 | na & na & na | low |  |  | 2.5
2013-03-22 | 9:00 | 25 | 8.2 | na & na & na | low |  |  | 0.82
2013-03-22 | 9:30 | 25 | 8.2 | na & na & na | low |  |  | 10
2013-03-22 | 10:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 10:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 11:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 11:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 12:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 12:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 13:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 13:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 14:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 14:30 | 25 | 8.2 | na & na & na | low |  |  | 0.82
2013-03-22 | 15:00 | 25 | 8.2 | na & na & na | low |  |  | 10
2013-03-22 | 15:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 16:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 16:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 17:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 17:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 18:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 18:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 19:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 19:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 20:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 20:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 21:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 21:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 22:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 22:30 | 25 | 8.2 | na & na & na | low
2013-03-22 | 23:00 | 25 | 8.2 | na & na & na | low
2013-03-22 | 23:30 | 25 | 8.2 | na & na & na | low
2013-03-23 | 24:00 | 25 | 8.2 | na & na & na | low
2013-03-23 | 24:30 | 25 | 8.2 | na & na & na | low
2013-03-23 | 25:00 | 25 | 8.2 | na & na & na | low
2013-03-23 | 25:30 | 25 | 8.2 | na & na & na | low
2013-03-23 | 26:00 | 25 | 8.2 | na & na & na | low
2013-03-23 | 26:30 | 25 | 8.2 | na & na & na | low
2013-03-23 | 27:00 | 25 | 8.2 | na & na & na | low
2013-03-23 | 27:30 | 25 | 8.2 | na & na & na | low
2013-03-23 | 28:00 | 25 | 8.2 | na & na & na | low
2013-03-23 | 28:30 | 25 | 8.2 | na & na & na | low
2013-03-23 | 29:00 | 25 | 8.2 | na & na & na | low
2013-03-23 | 29:30 | 25 | 8.2 | na & na & na | low
2013-03-23 | 30:00 | 25 | 8.2 | na & na & na | low
2013-03-23 | 30:30 | 25 | 8.2 | na & na & na | low
2013-03-23 | 31:00 | 25 | 8.2 | na & na & na | low
2013-03-23 | 31:30 | 25 | 8.2 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 13
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-23 | 8:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 8:30 | 25 | 8.2 | na & na & na | low |  |  | 2.5
2013-04-23 | 9:00 | 25 | 8.2 | na & na & na | low |  |  | 0.82
2013-04-23 | 9:30 | 25 | 8.2 | na & na & na | low |  |  | 10
2013-04-23 | 10:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 10:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 11:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 11:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 12:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 12:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 13:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 13:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 14:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 14:30 | 25 | 8.2 | na & na & na | low |  |  | 0.82
2013-04-23 | 15:00 | 25 | 8.2 | na & na & na | low |  |  | 10
2013-04-23 | 15:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 16:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 16:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 17:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 17:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 18:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 18:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 19:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 19:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 20:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 20:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 21:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 21:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 22:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 22:30 | 25 | 8.2 | na & na & na | low
2013-04-23 | 23:00 | 25 | 8.2 | na & na & na | low
2013-04-23 | 23:30 | 25 | 8.2 | na & na & na | low
2013-04-24 | 24:00 | 25 | 8.2 | na & na & na | low
2013-04-24 | 24:30 | 25 | 8.2 | na & na & na | low
2013-04-24 | 25:00 | 25 | 8.2 | na & na & na | low
2013-04-24 | 25:30 | 25 | 8.2 | na & na & na | low
2013-04-24 | 26:00 | 25 | 8.2 | na & na & na | low
2013-04-24 | 26:30 | 25 | 8.2 | na & na & na | low
2013-04-24 | 27:00 | 25 | 8.2 | na & na & na | low
2013-04-24 | 27:30 | 25 | 8.2 | na & na & na | low
2013-04-24 | 28:00 | 25 | 8.2 | na & na & na | low
2013-04-24 | 28:30 | 25 | 8.2 | na & na & na | low
2013-04-24 | 29:00 | 25 | 8.2 | na & na & na | low
2013-04-24 | 29:30 | 25 | 8.2 | na & na & na | low
2013-04-24 | 30:00 | 25 | 8.2 | na & na & na | low
2013-04-24 | 30:30 | 25 | 8.2 | na & na & na | low
2013-04-24 | 31:00 | 25 | 8.2 | na & na & na | low
2013-04-24 | 31:30 | 25 | 8.2 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 14
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-24 | 8:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 8:30 | 25 | 8.2 | na & na & na | low |  |  | 2.5
2013-03-24 | 9:00 | 25 | 8.2 | na & na & na | low |  |  | 0.82
2013-03-24 | 9:30 | 25 | 8.2 | na & na & na | low |  |  | 10
2013-03-24 | 10:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 10:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 11:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 11:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 12:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 12:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 13:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 13:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 14:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 14:30 | 25 | 8.2 | na & na & na | low |  |  | 0.82
2013-03-24 | 15:00 | 25 | 8.2 | na & na & na | low |  |  | 10
2013-03-24 | 15:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 16:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 16:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 17:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 17:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 18:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 18:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 19:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 19:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 20:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 20:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 21:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 21:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 22:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 22:30 | 25 | 8.2 | na & na & na | low
2013-03-24 | 23:00 | 25 | 8.2 | na & na & na | low
2013-03-24 | 23:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 24:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 24:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 25:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 25:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 26:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 26:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 27:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 27:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 28:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 28:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 29:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 29:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 30:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 30:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 31:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 31:30 | 25 | 8.2 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 15
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-25 | 8:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 8:30 | 25 | 8.2 | na & na & na | low |  |  | 2.5
2013-03-25 | 9:00 | 25 | 8.2 | na & na & na | low |  |  | 0.82
2013-03-25 | 9:30 | 25 | 8.2 | na & na & na | low |  |  | 10
2013-03-25 | 10:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 10:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 11:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 11:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 12:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 12:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 13:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 13:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 14:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 14:30 | 25 | 8.2 | na & na & na | low |  |  | 0.82
2013-03-25 | 15:00 | 25 | 8.2 | na & na & na | low |  |  | 10
2013-03-25 | 15:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 16:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 16:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 17:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 17:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 18:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 18:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 19:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 19:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 20:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 20:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 21:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 21:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 22:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 22:30 | 25 | 8.2 | na & na & na | low
2013-03-25 | 23:00 | 25 | 8.2 | na & na & na | low
2013-03-25 | 23:30 | 25 | 8.2 | na & na & na | low
2013-03-26 | 24:00 | 25 | 8.2 | na & na & na | low
2013-03-26 | 24:30 | 25 | 8.2 | na & na & na | low
2013-03-26 | 25:00 | 25 | 8.2 | na & na & na | low
2013-03-26 | 25:30 | 25 | 8.2 | na & na & na | low
2013-03-26 | 26:00 | 25 | 8.2 | na & na & na | low
2013-03-26 | 26:30 | 25 | 8.2 | na & na & na | low
2013-03-26 | 27:00 | 25 | 8.2 | na & na & na | low
2013-03-26 | 27:30 | 25 | 8.2 | na & na & na | low
2013-03-26 | 28:00 | 25 | 8.2 | na & na & na | low
2013-03-26 | 28:30 | 25 | 8.2 | na & na & na | low
2013-03-26 | 29:00 | 25 | 8.2 | na & na & na | low
2013-03-26 | 29:30 | 25 | 8.2 | na & na & na | low
2013-03-26 | 30:00 | 25 | 8.2 | na & na & na | low
2013-03-26 | 30:30 | 25 | 8.2 | na & na & na | low
2013-03-26 | 31:00 | 25 | 8.2 | na & na & na | low
2013-03-26 | 31:30 | 25 | 8.2 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 16
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-26 | 8:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 8:30 | 25 | 9.84 | na & na & na | low |  |  | 2.5
2013-03-26 | 9:00 | 25 | 9.84 | na & na & na | low |  |  | 0.82
2013-03-26 | 9:30 | 25 | 9.84 | na & na & na | low |  |  | 10
2013-03-26 | 10:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 10:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 11:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 11:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 12:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 12:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 13:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 13:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 14:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 14:30 | 25 | 9.84 | na & na & na | low |  |  | 0.82
2013-03-26 | 15:00 | 25 | 9.84 | na & na & na | low |  |  | 12
2013-03-26 | 15:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 16:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 16:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 17:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 17:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 18:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 18:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 19:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 19:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 20:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 20:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 21:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 21:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 22:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 22:30 | 25 | 9.84 | na & na & na | low
2013-03-26 | 23:00 | 25 | 9.84 | na & na & na | low
2013-03-26 | 23:30 | 25 | 9.84 | na & na & na | low
2013-03-27 | 24:00 | 25 | 9.84 | na & na & na | low
2013-03-27 | 24:30 | 25 | 9.84 | na & na & na | low
2013-03-27 | 25:00 | 25 | 9.84 | na & na & na | low
2013-03-27 | 25:30 | 25 | 9.84 | na & na & na | low
2013-03-27 | 26:00 | 25 | 9.84 | na & na & na | low
2013-03-27 | 26:30 | 25 | 9.84 | na & na & na | low
2013-03-27 | 27:00 | 25 | 9.84 | na & na & na | low
2013-03-27 | 27:30 | 25 | 9.84 | na & na & na | low
2013-03-27 | 28:00 | 25 | 9.84 | na & na & na | low
2013-03-27 | 28:30 | 25 | 9.84 | na & na & na | low
2013-03-27 | 29:00 | 25 | 9.84 | na & na & na | low
2013-03-27 | 29:30 | 25 | 9.84 | na & na & na | low
2013-03-27 | 30:00 | 25 | 9.84 | na & na & na | low
2013-03-27 | 30:30 | 25 | 9.84 | na & na & na | low
2013-03-27 | 31:00 | 25 | 9.84 | na & na & na | low
2013-03-27 | 31:30 | 25 | 9.84 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 17PQM
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-27 | 8:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 8:30 | 27.5 | 10.66 | na & na & na | low |  |  | 2.5
2013-03-27 | 9:00 | 27.5 | 10.66 | na & na & na | low |  |  | 0.82
2013-03-27 | 9:30 | 27.5 | 10.66 | na & na & na | low |  |  | 11
2013-03-27 | 10:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 10:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 11:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 11:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 12:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 12:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 13:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 13:30 | 27.5 | 10.66 | na & na & na | low |  |  | PQM In progress
2013-03-27 | 14:00 | 27.5 | 10.66 | na & na & na | low |  |  | Wind control in operation
2013-03-27 | 14:30 | 27.5 | 10.66 | na & na & na | low |  |  | 0.82
2013-03-27 | 15:00 | 27.5 | 10.66 | na & na & na | low |  |  | 13
2013-03-27 | 15:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 16:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 16:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 17:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 17:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 18:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 18:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 19:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 19:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 20:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 20:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 21:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 21:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 22:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 22:30 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 23:00 | 27.5 | 10.66 | na & na & na | low
2013-03-27 | 23:30 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 24:00 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 24:30 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 25:00 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 25:30 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 26:00 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 26:30 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 27:00 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 27:30 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 28:00 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 28:30 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 29:00 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 29:30 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 30:00 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 30:30 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 31:00 | 27.5 | 10.66 | na & na & na | low
2013-03-28 | 31:30 | 27.5 | 10.66 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 18
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-28 | 8:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 8:30 | 27.5 | 11.48 | na & na & na | low |  |  | 2.5
2013-03-28 | 9:00 | 27.5 | 11.48 | na & na & na | low |  |  | 0.82
2013-03-28 | 9:30 | 27.5 | 11.48 | na & na & na | low |  |  | 11
2013-03-28 | 10:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 10:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 11:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 11:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 12:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 12:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 13:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 13:30 | 27.5 | 11.48 | na & na & na | low |  |  | PQM In progress
2013-03-28 | 14:00 | 27.5 | 11.48 | na & na & na | low |  |  | Wind control in operation
2013-03-28 | 14:30 | 27.5 | 11.48 | na & na & na | low |  |  | 0.82
2013-03-28 | 15:00 | 27.5 | 11.48 | na & na & na | low |  |  | 14
2013-03-28 | 15:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 16:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 16:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 17:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 17:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 18:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 18:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 19:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 19:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 20:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 20:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 21:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 21:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 22:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 22:30 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 23:00 | 27.5 | 11.48 | na & na & na | low
2013-03-28 | 23:30 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 24:00 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 24:30 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 25:00 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 25:30 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 26:00 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 26:30 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 27:00 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 27:30 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 28:00 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 28:30 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 29:00 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 29:30 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 30:00 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 30:30 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 31:00 | 27.5 | 11.48 | na & na & na | low
2013-03-29 | 31:30 | 27.5 | 11.48 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 19
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-29 | 8:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 8:30 | 27.5 | 12.3 | na & na & na | low |  |  | 2.5
2013-03-29 | 9:00 | 27.5 | 12.3 | na & na & na | low |  |  | 0.82
2013-03-29 | 9:30 | 27.5 | 12.3 | na & na & na | low |  |  | 11
2013-03-29 | 10:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 10:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 11:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 11:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 12:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 12:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 13:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 13:30 | 27.5 | 12.3 | na & na & na | low |  |  | PQM In progress
2013-03-29 | 14:00 | 27.5 | 12.3 | na & na & na | low |  |  | Wind control in operation
2013-03-29 | 14:30 | 27.5 | 12.3 | na & na & na | low |  |  | 0.82
2013-03-29 | 15:00 | 27.5 | 12.3 | na & na & na | low |  |  | 15
2013-03-29 | 15:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 16:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 16:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 17:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 17:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 18:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 18:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 19:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 19:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 20:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 20:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 21:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 21:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 22:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 22:30 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 23:00 | 27.5 | 12.3 | na & na & na | low
2013-03-29 | 23:30 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 24:00 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 24:30 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 25:00 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 25:30 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 26:00 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 26:30 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 27:00 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 27:30 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 28:00 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 28:30 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 29:00 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 29:30 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 30:00 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 30:30 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 31:00 | 27.5 | 12.3 | na & na & na | low
2013-03-30 | 31:30 | 27.5 | 12.3 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 20
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-30 | 8:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 8:30 | 27.5 | 13.12 | na & na & na | low |  |  | 2.5
2013-03-30 | 9:00 | 27.5 | 13.12 | na & na & na | low |  |  | 0.82
2013-03-30 | 9:30 | 27.5 | 13.12 | na & na & na | low |  |  | 11
2013-03-30 | 10:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 10:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 11:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 11:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 12:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 12:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 13:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 13:30 | 27.5 | 13.12 | na & na & na | low |  |  | PQM In progress
2013-03-30 | 14:00 | 27.5 | 13.12 | na & na & na | low |  |  | Wind control in operation
2013-03-30 | 14:30 | 27.5 | 13.12 | na & na & na | low |  |  | 0.82
2013-03-30 | 15:00 | 27.5 | 13.12 | na & na & na | low |  |  | 16
2013-03-30 | 15:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 16:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 16:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 17:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 17:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 18:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 18:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 19:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 19:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 20:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 20:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 21:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 21:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 22:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 22:30 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 23:00 | 27.5 | 13.12 | na & na & na | low
2013-03-30 | 23:30 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 24:00 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 24:30 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 25:00 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 25:30 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 26:00 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 26:30 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 27:00 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 27:30 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 28:00 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 28:30 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 29:00 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 29:30 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 30:00 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 30:30 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 31:00 | 27.5 | 13.12 | na & na & na | low
2013-03-31 | 31:30 | 27.5 | 13.12 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 21
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-03-31 | 8:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 8:30 | 27.5 | 13.94 | na & na & na | low |  |  | 2.5
2013-03-31 | 9:00 | 27.5 | 13.94 | na & na & na | low |  |  | 0.82
2013-03-31 | 9:30 | 27.5 | 13.94 | na & na & na | low |  |  | 11
2013-03-31 | 10:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 10:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 11:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 11:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 12:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 12:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 13:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 13:30 | 27.5 | 13.94 | na & na & na | low |  |  | PQM In progress
2013-03-31 | 14:00 | 27.5 | 13.94 | na & na & na | low |  |  | Wind control in operation
2013-03-31 | 14:30 | 27.5 | 13.94 | na & na & na | low |  |  | 0.82
2013-03-31 | 15:00 | 27.5 | 13.94 | na & na & na | low |  |  | 17
2013-03-31 | 15:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 16:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 16:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 17:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 17:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 18:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 18:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 19:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 19:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 20:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 20:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 21:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 21:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 22:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 22:30 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 23:00 | 27.5 | 13.94 | na & na & na | low
2013-03-31 | 23:30 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 24:00 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 24:30 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 25:00 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 25:30 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 26:00 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 26:30 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 27:00 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 27:30 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 28:00 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 28:30 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 29:00 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 29:30 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 30:00 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 30:30 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 31:00 | 27.5 | 13.94 | na & na & na | low
2013-04-01 | 31:30 | 27.5 | 13.94 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 22
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-01 | 8:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 8:30 | 27.5 | 15.58 | na & na & na | low |  |  | 2.5
2013-04-01 | 9:00 | 27.5 | 15.58 | na & na & na | low |  |  | 0.82
2013-04-01 | 9:30 | 27.5 | 15.58 | na & na & na | low |  |  | 11
2013-04-01 | 10:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 10:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 11:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 11:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 12:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 12:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 13:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 13:30 | 27.5 | 15.58 | na & na & na | low |  |  | PQM In progress
2013-04-01 | 14:00 | 27.5 | 15.58 | na & na & na | low |  |  | Wind control in operation
2013-04-01 | 14:30 | 27.5 | 15.58 | na & na & na | low |  |  | 0.82
2013-04-01 | 15:00 | 27.5 | 15.58 | na & na & na | low |  |  | 19
2013-04-01 | 15:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 16:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 16:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 17:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 17:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 18:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 18:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 19:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 19:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 20:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 20:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 21:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 21:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 22:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 22:30 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 23:00 | 27.5 | 15.58 | na & na & na | low
2013-04-01 | 23:30 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 24:00 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 24:30 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 25:00 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 25:30 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 26:00 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 26:30 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 27:00 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 27:30 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 28:00 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 28:30 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 29:00 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 29:30 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 30:00 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 30:30 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 31:00 | 27.5 | 15.58 | na & na & na | low
2013-04-02 | 31:30 | 27.5 | 15.58 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 23
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-02 | 8:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 8:30 | 27.5 | 0 | na & na & na | low |  |  | 2.5
2013-04-02 | 9:00 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-02 | 9:30 | 27.5 | 0 | na & na & na | low |  |  | 11
2013-04-02 | 10:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 10:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 11:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 11:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 12:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 12:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 13:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 13:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 14:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 14:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 15:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 15:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 16:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 16:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 17:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 17:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 18:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 18:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 19:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 19:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 20:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 20:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 21:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 21:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 22:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 22:30 | 27.5 | 0 | na & na & na | low
2013-04-02 | 23:00 | 27.5 | 0 | na & na & na | low
2013-04-02 | 23:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 24:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 24:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 25:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 25:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 26:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 26:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 27:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 27:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 28:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 28:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 29:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 29:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 30:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 30:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 31:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 31:30 | 27.5 | 0 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 24PQM TO WP
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-03 | 8:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 8:30 | 27.5 | 0 | na & na & na | low |  |  | 2.5
2013-04-03 | 9:00 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-03 | 9:30 | 27.5 | 0 | na & na & na | low |  |  | 11
2013-04-03 | 10:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 10:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 11:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 11:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 12:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 12:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 13:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 13:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 14:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 14:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 15:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 15:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 16:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 16:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 17:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 17:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 18:00 | 27.5 | 0 | na & na & na | low |  |  | Wind control in operation
2013-04-03 | 18:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 19:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 19:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 20:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 20:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 21:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 21:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 22:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 22:30 | 27.5 | 0 | na & na & na | low
2013-04-03 | 23:00 | 27.5 | 0 | na & na & na | low
2013-04-03 | 23:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 24:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 24:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 25:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 25:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 26:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 26:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 27:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 27:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 28:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 28:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 29:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 29:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 30:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 30:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 31:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 31:30 | 27.5 | 0 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 25
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-04 | 8:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 8:30 | 27.5 | 0 | na & na & na | low |  |  | 2.5
2013-04-04 | 9:00 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-04 | 9:30 | 27.5 | 0 | na & na & na | low |  |  | 11
2013-04-04 | 10:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 10:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 11:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 11:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 12:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 12:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 13:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 13:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 14:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 14:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 15:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 15:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 16:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 16:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 17:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 17:30 | 27.5 | 0 | na & na & na | low |  |  | Wind Control in operation
2013-04-04 | 18:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 18:30 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-04 | 19:00 | 27.5 | 0 | na & na & na | low |  |  | 18
2013-04-04 | 19:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 20:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 20:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 21:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 21:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 22:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 22:30 | 27.5 | 0 | na & na & na | low
2013-04-04 | 23:00 | 27.5 | 0 | na & na & na | low
2013-04-04 | 23:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 24:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 24:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 25:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 25:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 26:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 26:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 27:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 27:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 28:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 28:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 29:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 29:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 30:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 30:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 31:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 31:30 | 27.5 | 0 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 26
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-05 | 8:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 8:30 | 27.5 | 0 | na & na & na | low |  |  | 2.5
2013-04-05 | 9:00 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-05 | 9:30 | 27.5 | 0 | na & na & na | low |  |  | 11
2013-04-05 | 10:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 10:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 11:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 11:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 12:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 12:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 13:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 13:30 | 27.5 | -9 | na & na & na | low |  |  | (R5) Power factor test: 0.95 lagging (absorbing) (R11)
2013-04-05 | 14:00 | 27.5 | 9 | na & na & na | low |  |  | (R5) Power factor test: 0.95 leading (supplying) (R11)
2013-04-05 | 14:30 | 27.5 | -9 | na & na & na | low |  |  | (R6) Power factor ramp test: 0.95 lagging (absorbing)(R11)
2013-04-05 | 15:00 | 27.5 | 9 | na & na & na | low |  |  | (R6) Power factor ramp test: 0.95 leading (supplying)(R11)
2013-04-05 | 15:30 | 27.5 | 0 | na & na & na | low |  |  | (R12) Manual tap changing of the SUT to maintain correct HV set point voltage via the park controller.
2013-04-05 | 16:00 | 27.5 | 0 | na & na & na | low |  |  | MW set point to be issued by WPC to test communication, and observe wind farm response
2013-04-05 | 16:30 | 27.5 | 0 | na & na & na | low |  |  | (R18) 132kV voltage set point to be issued by WPC to test communication, and observe wind farm response
2013-04-05 | 17:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 17:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 18:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 18:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 19:00 | 27.5 | 0 | na & na & na | low |  |  | Wind Control in operation
2013-04-05 | 19:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 20:00 | 27.5 | 0 | na & na & na | low |  |  | 2.5
2013-04-05 | 20:30 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-05 | 21:00 | 27.5 | 0 | na & na & na | low |  |  | 18
2013-04-05 | 21:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 22:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 22:30 | 27.5 | 0 | na & na & na | low
2013-04-05 | 23:00 | 27.5 | 0 | na & na & na | low
2013-04-05 | 23:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 24:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 24:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 25:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 25:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 26:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 26:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 27:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 27:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 28:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 28:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 29:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 29:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 30:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 30:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 31:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 31:30 | 27.5 | 0 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 27
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-06 | 8:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 8:30 | 27.5 | 0 | na & na & na | low |  |  | 2.5
2013-04-06 | 9:00 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-06 | 9:30 | 27.5 | 0 | na & na & na | low |  |  | 11
2013-04-06 | 10:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 10:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 11:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 11:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 12:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 12:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 13:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 13:30 | 27.5 | 0 | na & na & na | low |  |  | PQM In progress
2013-04-06 | 14:00 | 27.5 | 0 | na & na & na | low |  |  | Wind control in operation
2013-04-06 | 14:30 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-06 | 15:00 | 27.5 | 0 | na & na & na | low |  |  | 19
2013-04-06 | 15:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 16:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 16:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 17:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 17:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 18:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 18:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 19:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 19:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 20:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 20:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 21:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 21:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 22:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 22:30 | 27.5 | 0 | na & na & na | low
2013-04-06 | 23:00 | 27.5 | 0 | na & na & na | low
2013-04-06 | 23:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 24:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 24:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 25:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 25:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 26:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 26:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 27:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 27:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 28:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 28:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 29:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 29:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 30:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 30:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 31:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 31:30 | 27.5 | 15.58 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 28
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-07 | 8:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 8:30 | 27.5 | 0 | na & na & na | low |  |  | 2.5
2013-04-07 | 9:00 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-07 | 9:30 | 27.5 | 0 | na & na & na | low |  |  | 11
2013-04-07 | 10:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 10:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 11:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 11:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 12:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 12:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 13:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 13:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 14:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 14:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 15:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 15:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 16:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 16:30 | 27.5 | 0 | na & na & na | low |  |  | Wind Control in operation
2013-04-07 | 17:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 17:30 | 27.5 | 0 | na & na & na | low |  |  | 2.5
2013-04-07 | 18:00 | 27.5 | 0 | na & na & na | low |  |  | 0.82
2013-04-07 | 18:30 | 27.5 | 0 | na & na & na | low |  |  | 20
2013-04-07 | 19:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 19:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 20:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 20:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 21:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 21:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 22:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 22:30 | 27.5 | 0 | na & na & na | low
2013-04-07 | 23:00 | 27.5 | 0 | na & na & na | low
2013-04-07 | 23:30 | 27.5 | 0 | na & na & na | low
2013-04-08 | 24:00 | 27.5 | 0 | na & na & na | low
2013-04-08 | 24:30 | 27.5 | 0 | na & na & na | low
2013-04-08 | 25:00 | 27.5 | 0 | na & na & na | low
2013-04-08 | 25:30 | 27.5 | 0 | na & na & na | low
2013-04-08 | 26:00 | 27.5 | 0 | na & na & na | low
2013-04-08 | 26:30 | 27.5 | 0 | na & na & na | low
2013-04-08 | 27:00 | 27.5 | 0 | na & na & na | low
2013-04-08 | 27:30 | 27.5 | 0 | na & na & na | low
2013-04-08 | 28:00 | 27.5 | 0 | na & na & na | low
2013-04-08 | 28:30 | 27.5 | 0 | na & na & na | low
2013-04-08 | 29:00 | 27.5 | 0 | na & na & na | low
2013-04-08 | 29:30 | 27.5 | 0 | na & na & na | low
2013-04-08 | 30:00 | 27.5 | 0 | na & na & na | low
2013-04-08 | 30:30 | 27.5 | 0 | na & na & na | low
2013-04-08 | 31:00 | 27.5 | 0 | na & na & na | low
2013-04-08 | 31:30 | 27.5 | 9.02 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 29
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2014-04-08 | 8:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 8:30 | 27.5 | 9.02 | na & na & na | low |  |  | 2.5
2014-04-08 | 9:00 | 27.5 | 9.02 | na & na & na | low |  |  | 0.82
2014-04-08 | 9:30 | 27.5 | 9.02 | na & na & na | low |  |  | 11
2014-04-08 | 10:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 10:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 11:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 11:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 12:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 12:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 13:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 13:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 14:00 | 27.5 | 9.02 | na & na & na | low |  |  | Wind Control in operation
2014-04-08 | 14:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 15:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 15:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 16:00 | 27.5 | 9.02 | na & na & na | low |  |  | 2.5
2014-04-08 | 16:30 | 27.5 | 9.02 | na & na & na | low |  |  | 0.82
2014-04-08 | 17:00 | 27.5 | 9.02 | na & na & na | low |  |  | 22
2014-04-08 | 17:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 18:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 18:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 19:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 19:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 20:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 20:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 21:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 21:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 22:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 22:30 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 23:00 | 27.5 | 9.02 | na & na & na | low
2014-04-08 | 23:30 | 27.5 | 9.02 | na & na & na | low |  |  | 2.5
2014-04-09 | 24:00 | 27.5 | 9.02 | na & na & na | low |  |  | 0.82
2014-04-09 | 24:30 | 27.5 | 9.02 | na & na & na | low |  |  | 22
2014-04-09 | 25:00 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 25:30 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 26:00 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 26:30 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 27:00 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 27:30 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 28:00 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 28:30 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 29:00 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 29:30 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 30:00 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 30:30 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 31:00 | 27.5 | 9.02 | na & na & na | low
2014-04-09 | 31:30 | 27.5 | 9.02 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 30CONSTRAINT
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-09 | 8:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 8:30 | 27.5 | 9.02 | na & na & na | low |  |  | 2.5
2013-04-09 | 9:00 | 27.5 | 9.02 | na & na & na | low |  |  | 0.82
2013-04-09 | 9:30 | 27.5 | 9.02 | na & na & na | low |  |  | 11
2013-04-09 | 10:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 10:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 11:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 11:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 12:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 12:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 13:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 13:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 14:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 14:30 | 27.5 | 9.02 | na & na & na | low |  |  | Wind Control in operation
2013-04-09 | 15:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 15:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 16:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 16:30 | 27.5 | 9.02 | na & na & na | low |  |  | 2.5
2013-04-09 | 17:00 | 27.5 | 9.02 | na & na & na | low |  |  | 0.82
2013-04-09 | 17:30 | 27.5 | 9.02 | na & na & na | low |  |  | 22
2013-04-09 | 18:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 18:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 19:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 19:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 20:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 20:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 21:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 21:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 22:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 22:30 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 23:00 | 27.5 | 9.02 | na & na & na | low
2013-04-09 | 23:30 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 24:00 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 24:30 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 25:00 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 25:30 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 26:00 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 26:30 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 27:00 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 27:30 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 28:00 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 28:30 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 29:00 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 29:30 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 30:00 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 30:30 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 31:00 | 27.5 | 9.02 | na & na & na | low
2013-04-10 | 31:30 | 27.5 | #VALUE! | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 31
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-10 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-10 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-10 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-10 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-10 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-10 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 32
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-11 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-11 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-11 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-11 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-11 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-11 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 33
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-12 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-12 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-12 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-12 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-12 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-12 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 34
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-13 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-13 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-13 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-13 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-13 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-13 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 35
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-14 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-14 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-14 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-14 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-14 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-14 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 36
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-15 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-15 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-15 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-15 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-15 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-15 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 37
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-16 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-16 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-16 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-16 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-16 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-16 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 38
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-17 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-17 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-17 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-17 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-17 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-17 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 39
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-18 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-18 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-18 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-18 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-18 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-18 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 40
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-19 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-19 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-19 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-19 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-19 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-19 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 41
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-20 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-20 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-20 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-20 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-20 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-20 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 42
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-21 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-21 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-21 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-21 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-21 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-21 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 43
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-22 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-22 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-22 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-22 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-22 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-22 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 44
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-23 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-23 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-23 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-23 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-23 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-23 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 45
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-24 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-24 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-24 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-24 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-24 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-24 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 46
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-25 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-25 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-25 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-25 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-25 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-25 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 47
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-26 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-26 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-26 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-26 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-26 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-26 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 48
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-27 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-27 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-27 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-27 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-27 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-27 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 49
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-28 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-28 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-28 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-28 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-28 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-28 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## Day 50
| COMMISSIONING TEST DAILY SCHEDULE | [7 empty] | COMMISSIONING TEST DAILY PROFILES
(Make copy of sheet and rename as required.)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of Test | Trading Interval Starting | Active Power (MW) | Reactive Power (MVAr) | 'na' 'na' 'na' or combination. | low medium or high | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2013-04-29 | 8:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 8:30 | 55 | 18.04 | na & na & na | low |  |  | 2.5
2013-04-29 | 9:00 | 55 | 18.04 | na & na & na | low |  |  | 0.82
2013-04-29 | 9:30 | 55 | 18.04 | na & na & na | low |  |  | 22
2013-04-29 | 10:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 10:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 11:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 11:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 12:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 12:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 13:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 13:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 14:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 14:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 15:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 15:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 16:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 16:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 17:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 17:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 18:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 18:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 19:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 19:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 20:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 20:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 21:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 21:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 22:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 22:30 | 55 | 18.04 | na & na & na | low
2013-04-29 | 23:00 | 55 | 18.04 | na & na & na | low
2013-04-29 | 23:30 | 55 | 18.04 | na & na & na | low
2013-04-30 | 24:00 | 55 | 18.04 | na & na & na | low
2013-04-30 | 24:30 | 55 | 18.04 | na & na & na | low
2013-04-30 | 25:00 | 55 | 18.04 | na & na & na | low
2013-04-30 | 25:30 | 55 | 18.04 | na & na & na | low
2013-04-30 | 26:00 | 55 | 18.04 | na & na & na | low
2013-04-30 | 26:30 | 55 | 18.04 | na & na & na | low
2013-04-30 | 27:00 | 55 | 18.04 | na & na & na | low
2013-04-30 | 27:30 | 55 | 18.04 | na & na & na | low
2013-04-30 | 28:00 | 55 | 18.04 | na & na & na | low
2013-04-30 | 28:30 | 55 | 18.04 | na & na & na | low
2013-04-30 | 29:00 | 55 | 18.04 | na & na & na | low
2013-04-30 | 29:30 | 55 | 18.04 | na & na & na | low
2013-04-30 | 30:00 | 55 | 18.04 | na & na & na | low
2013-04-30 | 30:30 | 55 | 18.04 | na & na & na | low
2013-04-30 | 31:00 | 55 | 18.04 | na & na & na | low
2013-04-30 | 31:30 | 55 | 18.04 | na & na & na | low
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2013-03-04 | 2013-04-29 |  | na | low | C1 | S1
|  |  |  | na | medium | C2A | S2
|  |  |  | na | high | C2B | S3
|  |  |  | na & na |  | C3A | S4
|  |  |  | na & na |  | C3B | S5
|  |  |  | na & na |  | C4 | S6
|  |  |  | na & na & na |  | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13