| Introduction | The Industry Transition and Cutover Focus Group (ITCFG) face to face meeting held on Thursday 17 August to document an optional staged approach for New Connections, whereby retailers could allocate New Connection to LNSPs for a longer window. This approach is relevant for ACT, South Australia, Queensland, Tasmania and NSW jurisdictions with Victoria unaffected (pending OIC to defer metering competition). The following approach would require a Letter of No Action from the AER, agreement from the LNSP and in NSW a change to statutory arrangements allowing ASPs to continue metering services post 1 December. ITCFG briefly considered the possible need for a staged approach to address faulty meters. The general consensus and understanding by ITCFG was that the DB would continue to replace any faulty meters that they identify up until 30 November 2017. Any meters that are identified as faulty post the 1 December 2017 will require a notification to be sent to the Retailers as per the NER. No additional requirements where identified. The ITCFG did not review or discuss optional staged approach for other market process. The ITCFG has previously worked through each B2M (MSATS) and B2B transaction as part of a detailed transition activity planning. These include; - all MSATS Change Requests, - Customer and Site Details, - Meter Data Process (Meter Data Notification, Provide Meter Data and Verify Meter Data) - One Way Notification and - Service Orders (Re-Energisations, De-Energisations, Special Reads, Allocate NMI, New Connections (by jurisdiction), Add and Alts, Metering Investigation, Meter Reconfiguration & Supply Abolishment). |
| --- | --- |
| Proposed Staged Approach | New Connection – Local Network Service Provider nominated as RP, MDP and MPB (install a Type 5 or Type 6 metering) - New Connection Service Order Requests can be raised to the LNSP up until the 30/11/2017. - New Connection Service Order Requests not able to be completed by the 31/03/2018, will be responded to with a “Not Completed” SO Response with an ExceptionCode of “Service Provider Cancellation”. - In NSW, ASP’s will also continue to meter and service post 01/12/2017 for requests received prior to 30/11/2017. - New Connection Service Order Requests that were “Not Completed” with a NMI already established within MSATS but not yet connected, would require role updates (MC, MPB, MDP) by the retailer. This will need to be managed via the appropriate MSATS Change Request transaction rather than making the NMI extinct. - New Connection Service Order Responses post 1 December 2017 will be issued in the new schema version r36. - Retailer initiated New Connection Service Order Cancellations raised post 01/12/2017 will be sent via email using a Service Order Cancellation Template. |
| Problems Staged Approach seeks to address | - New Connection not being completed during a heightened period of activity. - Negative customer experience. - Avoid the use of manual processes as jobs could get lost - Smaller amount of cancellations that the DB’s will have to perform - No arrangements in place to have metering installed prior to and just after the Christmas period. - ASP’s may only complete part of the job if the job is still open at 01/12/2017 (large) - ASP’s may already have jobs scheduled to be completed post 01/12/2017 |
| Benefits | - Mitigates New Connection not being completed. - Provides some assurance that for the peak period up until Christmas customers will be connected. |
| Risks | - Changes to DB processes - Type 5 & 6 Meter stock reduced - Some DB’s have put in final orders for meters, may be able to extend that final order to cover until March. - Some DB’s have ended metering supply contracts and have stopped ordering. - Clear indication needs to be provided to metering suppliers by the end of this month. - Meter stocks may not be available from suppliers. - Distribution Metering Technician workforce reduced. - Manual processes on the DB’s side as systems have been configured for new 1 Dec obligations. - Legislative bill in NSW Advance Meter Bill will need to be reviewed and amended. - Compliance program for NSW DB’s for ASP’s will need to be reviewed and amended. - Changes to scripting to ASP’s on the permission to connect form. ASP’s will have two processes after the 1 December. - Re-education process to ASP’s, REC’s and distribution field force. - Re-instate old work flow process, this will create dual processes running in parallel. - Possible back office staff reductions need to be reviewed. - Installing meters by DB’s breaches the NER and they may not put themselves in that position even though there is a letter of no action. - DB’s may incur more costs as the customer has been quoted on a type 6 meter but they may have to install a type 5 meter. - All DB’s do not take part in this transition. |