# POC Industry Cutover Schedule (Timetable) and Responsibilities

| Step | Event | Market Time/EST | Responsible Party |
| --- | --- | --- | --- |
| 1. | Participants cease generating and sending Low & Med priority outbound transactions (Service Orders, Provide or Verify Meter Data requests, One Way Notifications and CDR/CSDN) | Friday 01/12/2017 13:00 (Local time or refer to B2B Procedures Version 2.2) | All Participants |
| 2. | Participants cease generating and sending High Priority Same Day Re-Energisations (per Jurisdictional reqmts) & Re-Energisation/De-Energisation Cancellations. | Friday 01/12/2017 a. 2:00pm in ACT b. 1:00pm in Queensland c. 4.00pm in Tasmania (Or refer to B2B Procedures Version 2.2) | All Participants |
| 3. | Participants cease sending Meter Data Notifications. | Friday 01/12/2017 17:00 AEST | All Participants |
|  | Receipt of MDM Settlement Data | Friday 01/12/2017 17:00 AEST | All Participants |
| 4. | Participants clear both incoming and outgoing from their B2B Inbox & Outbox All transactions processed | Friday 01/12/2017 Before 18:00 AEST | All Participants |
| 5. | Via Teleconference: - Advise all gateways are cleared of transactions - Advise readiness to continue onto next Cut-over step. | Friday 01/12/17 18:00 AEST | All Participants & AEMO |
| 6. | AEMO shuts down B2B Batch Handler | Friday 01/12/2017 18:00 AEST | AEMO |
| 7. | AEMO shuts down MSATS Batch Handler | Friday 01/12/2017 18:00 AEST | AEMO |
| 8. | Send transaction list to participants detailing remaining transactions in B2B Inbox & Outbox List to be published via email to all participants. | Friday 01/12/2017 Before 19:00 AEST | AEMO Should this be provided multiple times? If so, when? |
| 9. | Via Teleconference: - Advise issues that may impact on PVT or next milestone - Advise mitigation steps – if required - Advise next Milestone | Friday 01/12/2017 23:00 AEST | All Participants & AEMO |
| 10. | Via Teleconference: - Advise issues that may impact on PVT or next milestone - Advise mitigation steps – if required - Advise next Milestone | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 11. | Via Teleconference: - Advise issues that may impact on PVT or next milestone - Advise mitigation steps – if required - Advise next Milestone | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 12. | Via Teleconference: - Advise issues that may impact on PVT or next milestone - Advise mitigation steps – if required - Advise next Milestone | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 13. | Via Teleconference: - Advise issues that may impact on PVT or next milestone - Advise mitigation steps – if required - Advise next Milestone | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 14. | AEMO brings MSATS GUI back up - AEMO to notify MSATS GUI is available | <Day> <Date> <Time> AEST | AEMO |
| 15. | Participants able to change from FTP to API AEMO to confirm when the portal will be available for participants to obtain API key Current Schedule is SMP will be available to obtain API Keys on Tuesday 21 November 2017. This is to be confirmed. | <Day> <Date> <Time> AEST | Participants |
| 16. | Via Teleconference: - Participants to provide an update on Cut-over progress - Advise readiness to perform PVT @ <Time> | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 17. | Send transaction list to participants detailing transactions in B2B Inbox & Outbox List to be published via email to all participants. | Saturday 02/12/2017 Before 18:00 AEST | AEMO |
| 18. | AEMO brings B2B Batch Handler back up | Saturday 02/12/2017 18:00 AEST | AEMO |
| 19. | AEMO brings MSATS Batch Handler back up | Saturday 02/12/2017 18:00 AEST | AEMO |
| 20. | - Perform any internal troubleshooting period allowed to validate gateways/APIs are operational, etc. | <Day> <Date> <Time> AEST | Participants |
| 21. | Via Teleconference: - Advise readiness to start Production Verification Testing | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 22. | Perform Production Verification Testing | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 23. | Via Teleconference: - Participants to provide feedback on Production Verification Testing | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 24. | Systems in Production - All B2B transactions sent with R36 schema - All MSATS Transactions sent with R35 schema | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 25. | AEMO to start resending B2M notifications. Cancelled MSATS CRs notifications issued to affected Participants. | <Day> <Date> <Time> AEST | AEMO |
| 26*. | Participants to commence processing and sending backlog of Data – catch up processes include transactions Participants put on hold prior to and during Industry Cutover. | <Day> <Date> <Time> AEST | All Participants |
| 27*. | AEMO runs BCT processes updating role changes | <Day> <Date> <Time> AEST | All Participants & AEMO |
| 28*. | Recipient of BCT notifications to commence processing updates | <Day> <Date> <Time> AEST | Participants |
| 29*. | Participants raise role change CRs | <Day> <Date> <Time> AEST | Participants |

*Steps 26, 27, 28 & 29 can occur concurrently

All times (related to the conduct of the work for B2B Service Orders) refer to the local time for the Site (where the work requested is to be carried out). Local time is inclusive of daylight saving time changes.