## Slide 1: PROGRAM CONSULTATIVE FORUM Meeting pack
DATE: Tuesday 4 July 2017
TIME: 12.00 PM – 2.00 PM (AEST)
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI
TELECONFERENCE: DIAL IN: 1800 055 132; PIN: 35175886
CONTACT: poc@aemo.com.au

## Slide 2: Power of Choice PROGRAM UPDATE

## Slide 3: Actions from previous meeting
# | Description | Date due | Status | Owner | Comments/Outcomes
A04 | M Norris to share copy of Ergon’s handbook to other attendees. | 07 Jul 17 | Open | Ergon | 
A05 | LNSPs to circulate to all retailers draft’s T&C’s (per 11.86.7 of the new Rules) and any associated publications that they are developing (for example a ‘Retailer Handbook’) with industry. | 07 Jul 17 | Open | LNSPs | • Note: Vic LNSPs requirements to develop T&C’s may differ resulting from Victorian Order-in-Council
A06 | Industry Test Lead to report at next PCF on progress of testing. | 04 Jul 17 | Open | AEMO (ITWG Lead) | 
A07 | B. Healy to circulate test results publishing on HPQC. | 07 Jul 17 | Closed | AEMO | • Circulated via email on date 23 Jun 17
A08 | Testing results to be included in PCF pack monthly | 04 Jul 17 | Closed | AEMO | • Circulated via email on date 23 Jun 17
A09 | AEMO to speak to AEMC regarding communications, potentially with the AER. | 04 Jul 17 | Closed | AEMO | • AER/AEMC/AEMO have discussed the possibility of a joint communication.
A10 | LNSPs to circulate to all retailers ‘end of life meter replacement programs’ for existing fleets to facilitate adequate retailer and MC planning by Friday 7th July. | 07 Jul 17 | Open | LNSPs (non-Victorian) | • Note: Vic LNSPs not required as a result of Victorian decision to delay metering competition.
A11 | Retailers / LNSPs to provide forecasts of new connections over the period of December to February to feed into transition and cut-over planning and contingency planning activities. | 07 Jul 17 | Open | LNSPs / Retailers | 
A12 | LNSPs to provide example of corrective works program undertaken to rectify customer supply as a result of a natural disaster. Example program to focus on metering installations. | 07 Jul 17 | Open | LNSPs | • Information to include: number of meters (destroyed/replaced) rate of meter installations (qty per month), qty of new connections (i.e. complete re-builds), timeframe for meter rectification. Useful Examples could include cyclone Debbie 2017, Black Saturday Victoria 2009 (4,029 homes / structures destroyed).

## Slide 4: AEMO Program Update
General:
PoC Exec Forum
PWC activities scheduled to commence 4 July 2017
Commonwealth/AEMO pursuing notice of jurisdictional ‘x’ values
Waiting for Victorian Government to circulate the draft Order in Council - at this stage no changes to procedures are anticipated.
AEMO Procedures
AEMO Procedure pack 3 submission closed on 27 June
Final determination will be published on or before 30 November 2017
B2B Procedures
Verbal update on outcomes of meeting held Friday 30 June
The B2B Working Group has a compiled a log of small clarifications and corrections which AEMO will publish on the IECs behalf.
Current list is available on AEMO website Power of Choice B2B consultation
Any suggested improvements or changes not identified as error corrections will be the subject to a consultation in 2018.

## Slide 5: AEMO Program Update
Systems
Released B2B R36 and e-hub API’s to pre-prod on 13 June
Held SWG on 15 June
  Discussed B2B SMP tech guide & MSATS Tech guide
  Release an update (including schedule) on validation module on 26 June
ASWG completing an approval of R37 schema
Readiness:
Industry Testing Planning:
  Industry Testing Strategy – completed
  EN/MC Testing (Phase 1) – completed
  B2B Testing (Phase 2) – underway
  Market Trial (Phase 3) – final test plan published –commences 21 August
Accreditation and Registration Industry Plan – final version has been published
  Encourage to promptly commence any registration / accreditation activities
Transition and Cutover – planning discussions are continuing with the Readiness Working Group
  All B2M transactions have mapped (i.e. identified activities before, during and after)
  Majority of B2B have been mapped (exception of PMD/VMD/MDN)

## Slide 6: AEMO Program Update – upcoming MEETINGS / FORUMS
Program:
Executive Forum 25th July 2017
PCF next session will be held 27th July 2017
IEC meeting 1st August 2017
Systems:
Next SWG meeting is 17th July 2017
Readiness:
Industry testing WG 5th July 2017
ITCFG 11th & 12th July 2017
B2B WG:
B2B-WG 26th July 2017

## Slide 7: Industry Issues Register
System cut-over:
Industry raised an issue for discussion:
  Current assumptions are that the existing market arrangements and systems will cease to operate on Thursday 30 November, new arrangements (Rules, Procedures etc.) will commence morning of Friday 1st December.
  In effect, an overnight cut-over.
Discussion:
  Participants have advised a range of systems outage timings spanning from 12 to 48+ hours.
  Participants raised impacts to month end processes.
Actions taken:
AEMO seeking feedback on a proposed cut-over period spanning COB Friday 2 December to commencement of business, Monday 4 December.
Industry feedback provided by Wednesday, 26 May 2017.
AEMO discussing with AER approaches that may be required to give effect to a weekend system cut-over

## Slide 8: Watching briefs
Translation Tool
  No change to current planned delivery of the translation tool by mid-August to support any testing requirements

## Slide 9: Power of Choice Readiness update Industry Readiness Reporting

## Slide 10: Market readiness update
Market Readiness
Industry Readiness Reporting:
  June report has been published – received 40 participant reports (up 5 from May). Click here to access Industry Readiness Reports on AEMO’s website.
Accreditation and Registration:
  Published an updated version of the B2B e-Hub Accreditation Revocation Process on 19 June.
Industry Testing:
  Phase 1 testing (EN/MC changes) – Cycle 2 successfully completed. Cycle 3 in progress and scheduled to conclude on 30 June.
  Phase 2 testing (B2B) – test window from 19 June to 28 July.
  Phase 3 testing (Market Trial) – scheduled to commence on 21 August.
Transition & Cutover:
  Industry Transition & Cutover Focus Group (ITCGF) has held 6 meetings (next meeting is 3 July).
  All B2M and the majority of B2B transactions have been covered and the activities before, during and post cutover has been mapped out.
  ITCFG will continue to develop the POC Industry Transition & Cutover Plan (initial draft expected to be ready by the start of September).
  Verbal Update AEMO

## Slide 11: June 2017 READINESS REPORT
Summary:
Project status remains amber in June 2017:
  Status of “at risk” of achieving project deliverables on schedule.
  Progress remains at approximately 30%.
  Risk rating increased to “High”.
Participant categories:
  Retailer and Distributors are mainly reporting amber (“at risk”) with a medium or high risk rating.
  Meter Providers, Meter Data Providers and prospective Metering Coordinators mainly reporting amber or red (“not within schedule”) with a medium or high risk rating.
  Prospective Embedded Network Managers mainly reporting green or amber, with a low or medium risk rating.
  AEMO overall reporting green (“within schedule”) with medium risk rating.

## Slide 12: JUNE 2017 READINESS REPORT
Highlighted risks:
Amber progress status relates primarily to constrained timelines for delivery:
  Compressed timeframes for system design, build and testing.
  Compressed timeframes for registration and accreditation – including e-hub accreditation.
  Compressed timeframes for transition and cutover planning.
  Number and complexity of commercial arrangements to be updated.
Issues contributing to the High risk rating include:
  Uncertainties in operation of business processes (e.g. meter churn), distribution business' faults and emergencies processes, Victorian OIC.
  Uncertainties in transition and cutover activities and the timing of cutover.
  Lack of clarity on safety regulations.
  Number and level of maturity of competitive metering providers, Metering Coordinators and Embedded Network Managers.
Mitigating actions include:
  AEMO progressing industry test planning, with detailed Market Trial planning ongoing.
  The Industry Transition and Cutover Focus Group is meeting regularly and progressing planning on schedule.
  AEMO is continuing to reach out to industry participants to engage in the POC program.
  Participants encouraged to commence registration and accreditation activities.
  AEMO is chairing a PCF Industry Risk Meeting on 22 June 2017

## Slide 13: JUNE 2017 READINESS REPORT
Number of submissions:
40 reports received in total representing the following participant roles (increased from 35 in May):
  19 retailers (increased from 18)
  13 distribution businesses (includes initial MC, MP and MDP)
  8 metering companies (MPD, MP) (increased from 5)
  8 metering coordinators (MC) (increased from 5)
  4 embedded network manager (ENM) (increased from 2)
Approximately 17 retailers are not yet taking part in industry reporting
Note that organisations can nominate for multiple roles and participants can submit combined reports (i.e. one report for two distribution businesses)

## Slide 14
Risk Register Review
See attached Risk Register

## Slide 15: Forward Meeting Plan
POC-PCF meeting dates | Dates
POC-PCF Meeting #1 | 16-Sep-16
POC-PCF Meeting #2 | 7-Oct-16
POC-PCF Meeting #3 | 15-Nov-16
POC-PCF Meeting #4 | 15-Dec-16
POC-PCF Meeting #5 | 13-Feb-17
POC-PCF Meeting #6 | 23-Feb-17
POC-PCF Meeting #7 | 23-Mar-17
POC-PCF Meeting #8 | 05-May-17
POC-PCF Meeting #9 | 09-Jun-17
POC-PCF Meeting #9A (risk) | 22-Jun-17
POC-PCF Meeting #10 | 04-Jul-17
POC-PCF Meeting #11 | 27-Jul-17
POC-PCF Meeting #12 | 24-Aug-17
POC-PCF Meeting #13 | 28-Sep-17
POC-PCF Meeting #14 | 26-Oct-17
POC-PCF Meeting #15 | 23-Nov-17
POC-PCF Meeting #16 | 14-Dec-17
Facilities:
Melbourne, Sydney, Brisbane, Adelaide offices
Video conference
Webinar (when required)