## Consultations Calendar
2024 Gas and Electricity Retail Consultations |  |  | Q1 2024 | [12 empty] | Q2 2024 | [12 empty] | Q3 2024 | [12 empty] | Q4 2024 | [13 empty] | Q1 2025 | [12 empty] | Q2 2025 | [12 empty] | Q3 2025 | [12 empty] | Q4 2025
Last updated: 6 November 2024 |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  | Sept |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
This spreadsheet is indicative only. Please refer to AEMO's website for authoritative consultation dates. |  | Cat | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5
 | time axis 2024-01-01 to 2025-12-29
Gas
2023 Package 6 (WA RMP changes)* (targted effective date mid Sept 2024) |  | P | bar: 2024-03-11 to 2024-09-16
2023 Package 4- (IN006-23, 007-24) Renewable Gas Integration (QLD, SA and NSW/ACT 3 March 2025* |  | P,S | bar: 2024-08-12 to 2024-12-02; 2025-03-03
2024 Package 1 (B2B system changes (IN001-24, 004-22, 002-22 and 005-24))* |  |  | 2024-06-24: IN004-22; 2024-08-26: IN002-22 (R2); 2024-09-23: IN001-24
IN008-24 - Transport Layer Security (TLS) update and amendments to several TP documents (All) | bar: 2024-09-23 to 2025-02-24
Updates to Approved Process (all except WA) | bar: 2024-09-30 to 2025-01-06; 2025-01-20
Electricity
MSATS, Metering Services, and Metrology
May 2024 REMP Consultation (MSR Package 1) |  | P,S | 2024-09-16: Consultation Delay
CATS and WIGS Amalgamation |  | P | bar: 2024-05-27 to 2024-06-10; 2024-09-16 to 2024-11-11
November 2024 Consolidation |  | P | bar: 2024-05-27 to 2024-06-10; 2024-10-14 to 2024-11-04
Package 2 MSR |  | P,S | bar: 2024-05-27 to 2024-06-10; 2025-02-03 to 2025-04-28
Package 3 MSR |  | P,S | bar: 2024-05-27 to 2024-06-10; 2025-04-07 to 2025-04-28
Flexible Trading Arrangements |  | P,S | bar: 2024-05-27 to 2024-06-10; 2025-04-07 to 2025-04-28
September 2024 Metrology Procedure Part B consolidation |  | P | bar: 2024-05-27 to 2024-06-10
Minor Amendment - Metrology Procedure Part B |  | P
Minor Amendment/Consolidation - IESS updates |  | P
Business to Business (B2B)
B2B Procedures v3.9 |  | P,S | 2024-09-16: Consultation Delay
Legend
Gas | Electricity
GMI | Initial consult
PPC | Draft det
IIR | Final det
AEMO Decision | IEC Recom
ERA Review / Approval (WA only) | AEMO Decision
Effective date
AEMO Review | AEMO Review
Consultation is completed
Consultation is withdrawn or postponed for current program of work
"Green text" = added post prioritisation session
Catagory= "P" = Procedure, "S" = System, "G" Guideline, "R" = Rules, "TBA" To be advised
* - see GAS Package details tab for more information about the changes
Click to view the National Energy Market (NEM) Reform Implementation Roadmap
^ CR means Change Request
# ASWG means AseXML Working Group
Target date when CR^ for ASWG# is due

## GAS Package details
Package id# | IN# | Description
2023 Package 4 | IN006-23 | Renewable Gas Integration (excluding Victoria) for STTM and Non STTM markets) (Proponent AEMC). QLD, SA and NSW/ACT (STTM). Effective 3 Mar 2025
2023 Package 4 | IN007-24 | Minor RMP changes for QLD, SA and NSW/ACT
2023 Package 6 | IN002-22W | Potential gap with clause 377B (2).
2023 Package 6 | IN002-21W | Anticipated Annual Consumption in WA. (Proponent AEMO).
2023 Package 6 | IN009-20W | Possible typographical error in append 4 (Auditor’s deed of undertaking) clause 9 of WA RMP. Reference to clause 359 should be clause 358.
2023 Package 6 | IN002-23W | Minor documentation errors with WA Technical Protocol​
2023 Package 6 | IN001-24W | Correct clause numbering in Appendix 2 of WA RMP
Partially Committed Packages
2024 Package 1 | IN001-24 | Adjustment of Address field lengths to align with AS 4590 and Electricity changes
| IN004-22 | Proposed Improvements to Network Tariff B2B Notification
| IN002/22 | Update Gas Estimation / Substitution Reason Codes.
| IN005-24 | Inclusion of Contract MDQ in Gas RoLR Transaction Customer and Site Details from FRB to RoLR (T1010)
2024 Package 2 | IN011/13 | RMP only changes for Non DTS interval metering to remove a potential regulatory gap.
| IN019/13 | Resolve potential metering obligations in light of past concerns in relation to conduct provision.
| IN006/20 | Definition of a Customer could be improved for all east coast jurisdiction to include exempt customers for other purposes under the procedures in the event an exempt seller is registered either as a Retailer or an SCU (Vic only).
| IN015/22 | Harmonise the definition of Heating Value within east coast RMP.
| IN003/24 | Participant Build Pack 2 (i) Glossary (ii) Usage Guide - Possible duplications, hence can we look at ways to minimise.
| IN004/24 | Participant Build Pack 2 - Glossary should be updated with entries for BAR and GRMS. Originally raised as part of 2023 Package 2 East Coast (IN001-23, IN005-23)
| IN001/21W | Redrafting – WA RMP clause 32 - Error Correction Notice

## Disclaimer
Please note: this consultations calendar is intended only as a rough guide of when AEMO will hold consultations. The dates are indicative only and are subject to change without notice. It will be updated only periodically, so there is no guarantee that the information contained therein is current. Authoritative consultation dates are published either in the relevant distribution lists for the consultative forums or in the Consultations section of AEMO's website:
Link